## Sheet1
Issue Key | Project | Summary | Assignee | Created | Updated | Status | Issue Type | Priority | Original Estimate (sec) | Time Spent (sec) | Sprint | Fix Version | Labels | Components | Reporter | Resolution | Due Date | Original Estimate (hrs) | Time Spent (hrs)
OPS-1 | OPS | Sample issue summary 1 | Alice | 2024-03-30 | 2024-04-01 | In Progress | Bug | Critical | 7200 | 2940 | Sprint 1 | v1.1 | analytics, refactor, urgent | Database | Heidi | Duplicate | 2024-05-01 | 2 | 0.82
PROJ-2 | PROJ | Sample issue summary 2 | Charlie | 2024-03-01 | 2024-03-02 | To Do | Bug | Medium | 133200 | 18398 | Sprint 1 | v1.1 | refactor, UI | Database | Eve | Duplicate | 2024-02-07 | 37 | 5.11
OPS-3 | OPS | Sample issue summary 3 | Alice | 2024-03-10 | 2024-03-11 | Review | Story | High | 129600 | 71086 | Sprint 2 | v1.1 | refactor | Database | Heidi | Fixed | 2024-01-22 | 36 | 19.75
OPS-4 | OPS | Sample issue summary 4 | Diana | 2024-03-31 | 2024-04-06 | In Progress | Bug | Critical | 133200 | 102341 | Sprint 2 | v2.0 | refactor, UI, urgent | Frontend | Grace | Unresolved | 2024-02-26 | 37 | 28.43
PROJ-5 | PROJ | Sample issue summary 5 | Charlie | 2024-01-25 | 2024-01-30 | Done | Story | High | 32400 | 13720 | Backlog | v1.1 | QA, urgent | Frontend | Heidi | Fixed | 2024-01-30 | 9 | 3.81
OPS-6 | OPS | Sample issue summary 6 | Charlie | 2024-01-31 | 2024-01-31 | In Progress | Bug | Low | 82800 | 32211 | Backlog | v1.0 | refactor, QA | Frontend | Heidi | Fixed | 2024-04-15 | 23 | 8.95
PROJ-7 | PROJ | Sample issue summary 7 | Bob | 2024-03-23 | 2024-03-31 | Done | Task | High | 90000 | 6604 | Sprint 1 | v2.0 | QA, backend, UI | Database | Eve | Unresolved | 2024-04-15 | 25 | 1.83
PROJ-8 | PROJ | Sample issue summary 8 | Diana | 2024-03-20 | 2024-03-27 | Review | Bug | Low | 10800 | 6708 | Sprint 2 | v1.1 | analytics, urgent | API | Heidi | Won't Fix | 2024-04-26 | 3 | 1.86
PROJ-9 | PROJ | Sample issue summary 9 | Alice | 2024-04-05 | 2024-04-11 | To Do | Bug | Critical | 64800 | 38863 | Sprint 2 | v1.0 | analytics, backend, UI | Integration | Eve | Duplicate | 2024-05-02 | 18 | 10.8
PROJ-10 | PROJ | Sample issue summary 10 | Diana | 2024-03-08 | 2024-03-16 | Review | Story | Medium | 129600 | 120423 | Sprint 2 | v1.1 | QA, analytics | Integration | Grace | Unresolved | 2024-02-18 | 36 | 33.45
OPS-11 | OPS | Sample issue summary 11 | Bob | 2024-01-04 | 2024-01-05 | Review | Story | Medium | 75600 | 45618 | Sprint 3 | v1.1 | refactor, analytics, QA | Database | Frank | Unresolved | 2024-03-23 | 21 | 12.67
PROJ-12 | PROJ | Sample issue summary 12 | Charlie | 2024-02-08 | 2024-02-16 | In Progress | Bug | Low | 21600 | 17313 | Sprint 3 | v1.0 | urgent, backend | Integration | Heidi | Unresolved | 2024-02-13 | 6 | 4.81
OPS-13 | OPS | Sample issue summary 13 | Bob | 2024-04-12 | 2024-04-22 | Done | Task | High | 115200 | 10032 | Sprint 3 | v2.0 | backend, QA | Frontend | Eve | Won't Fix | 2024-02-04 | 32 | 2.79
PROJ-14 | PROJ | Sample issue summary 14 | Alice | 2024-02-04 | 2024-02-13 | Done | Story | Critical | 50400 | 6170 | Sprint 1 | v1.1 | analytics, QA | Database | Grace | Duplicate | 2024-02-12 | 14 | 1.71
OPS-15 | OPS | Sample issue summary 15 | Diana | 2024-01-26 | 2024-01-29 | Done | Task | Medium | 68400 | 48545 | Sprint 1 | v1.0 | urgent | API | Grace | Won't Fix | 2024-03-07 | 19 | 13.48
OPS-16 | OPS | Sample issue summary 16 | Charlie | 2024-02-24 | 2024-02-27 | In Progress | Story | Medium | 64800 | 32112 | Sprint 2 | v2.0 | urgent, refactor | API | Eve | Unresolved | 2024-03-26 | 18 | 8.92
DEV-17 | DEV | Sample issue summary 17 | Diana | 2024-01-05 | 2024-01-08 | In Progress | Story | Low | 115200 | 21452 | Sprint 1 | v1.1 | refactor, analytics | API | Heidi | Unresolved | 2024-03-22 | 32 | 5.96
DEV-18 | DEV | Sample issue summary 18 | Diana | 2024-04-15 | 2024-04-18 | In Progress | Story | Medium | 43200 | 24539 | Sprint 2 | v2.0 | urgent, QA, refactor | Frontend | Frank | Duplicate | 2024-01-24 | 12 | 6.82
DEV-19 | DEV | Sample issue summary 19 | Charlie | 2024-01-12 | 2024-01-19 | To Do | Story | Critical | 122400 | 73278 | Sprint 1 | v1.0 | UI | Integration | Frank | Fixed | 2024-05-17 | 34 | 20.36
OPS-20 | OPS | Sample issue summary 20 | Alice | 2024-03-19 | 2024-03-26 | In Progress | Task | Critical | 14400 | 5295 | Sprint 2 | v1.0 | UI, urgent | Integration | Frank | Duplicate | 2024-02-24 | 4 | 1.47
DEV-21 | DEV | Sample issue summary 21 | Bob | 2024-04-14 | 2024-04-20 | Done | Bug | Medium | 129600 | 2967 | Sprint 1 | v1.0 | QA | Database | Grace | Fixed | 2024-02-21 | 36 | 0.82
DEV-22 | DEV | Sample issue summary 22 | Alice | 2024-03-31 | 2024-04-06 | In Progress | Task | Critical | 136800 | 123480 | Sprint 1 | v1.0 | analytics, backend | Backend | Heidi | Won't Fix | 2024-01-27 | 38 | 34.3
OPS-23 | OPS | Sample issue summary 23 | Bob | 2024-03-31 | 2024-04-07 | Review | Bug | High | 68400 | 37960 | Sprint 3 | v2.0 | urgent, analytics, UI | Backend | Frank | Duplicate | 2024-05-17 | 19 | 10.54
DEV-24 | DEV | Sample issue summary 24 | Alice | 2024-04-05 | 2024-04-08 | In Progress | Story | Medium | 7200 | 5502 | Sprint 2 | v1.1 | UI, refactor | Integration | Frank | Fixed | 2024-03-30 | 2 | 1.53
PROJ-25 | PROJ | Sample issue summary 25 | Bob | 2024-04-07 | 2024-04-13 | Review | Task | High | 111600 | 85618 | Sprint 3 | v2.0 | backend, analytics, urgent | API | Eve | Unresolved | 2024-04-14 | 31 | 23.78
PROJ-26 | PROJ | Sample issue summary 26 | Alice | 2024-04-15 | 2024-04-20 | Review | Bug | Low | 75600 | 34371 | Sprint 2 | v1.0 | urgent | Integration | Frank | Duplicate | 2024-05-13 | 21 | 9.55
OPS-27 | OPS | Sample issue summary 27 | Diana | 2024-04-09 | 2024-04-18 | In Progress | Task | Critical | 21600 | 1174 | Backlog | v2.0 | urgent, UI, QA | API | Grace | Duplicate | 2024-01-30 | 6 | 0.33
PROJ-28 | PROJ | Sample issue summary 28 | Bob | 2024-03-15 | 2024-03-20 | In Progress | Bug | Critical | 86400 | 74066 | Backlog | v1.1 | analytics, UI, urgent | Frontend | Grace | Fixed | 2024-02-04 | 24 | 20.57
OPS-29 | OPS | Sample issue summary 29 | Charlie | 2024-03-23 | 2024-03-25 | In Progress | Story | Medium | 97200 | 43307 | Backlog | v1.1 | urgent | Frontend | Grace | Unresolved | 2024-03-04 | 27 | 12.03
DEV-30 | DEV | Sample issue summary 30 | Charlie | 2024-01-09 | 2024-01-19 | Done | Bug | Critical | 82800 | 65566 | Sprint 3 | v1.1 | UI, urgent, backend | Integration | Frank | Unresolved | 2024-03-26 | 23 | 18.21
DEV-31 | DEV | Sample issue summary 31 | Charlie | 2024-04-20 | 2024-04-28 | To Do | Task | Low | 36000 | 12368 | Sprint 2 | v1.1 | backend | API | Heidi | Unresolved | 2024-04-04 | 10 | 3.44
DEV-32 | DEV | Sample issue summary 32 | Bob | 2024-02-01 | 2024-02-10 | In Progress | Story | High | 118800 | 81918 | Sprint 3 | v1.1 | refactor, analytics, QA | Backend | Frank | Duplicate | 2024-01-26 | 33 | 22.75
PROJ-33 | PROJ | Sample issue summary 33 | Charlie | 2024-03-11 | 2024-03-12 | Review | Story | Low | 18000 | 7479 | Sprint 1 | v1.1 | refactor, analytics, backend | Integration | Eve | Fixed | 2024-03-14 | 5 | 2.08
PROJ-34 | PROJ | Sample issue summary 34 | Alice | 2024-03-05 | 2024-03-11 | In Progress | Bug | Low | 18000 | 1392 | Backlog | v2.0 | QA | Database | Heidi | Duplicate | 2024-04-06 | 5 | 0.39
DEV-35 | DEV | Sample issue summary 35 | Bob | 2024-03-03 | 2024-03-10 | In Progress | Task | High | 140400 | 24562 | Sprint 2 | v1.1 | analytics | Integration | Frank | Unresolved | 2024-03-21 | 39 | 6.82
PROJ-36 | PROJ | Sample issue summary 36 | Diana | 2024-03-13 | 2024-03-22 | Review | Task | Low | 104400 | 95032 | Backlog | v1.0 | analytics | Frontend | Heidi | Duplicate | 2024-04-08 | 29 | 26.4
DEV-37 | DEV | Sample issue summary 37 | Bob | 2024-04-20 | 2024-04-26 | In Progress | Bug | Medium | 104400 | 48230 | Sprint 1 | v1.1 | urgent, UI | API | Heidi | Duplicate | 2024-01-22 | 29 | 13.4
PROJ-38 | PROJ | Sample issue summary 38 | Diana | 2024-04-21 | 2024-05-01 | In Progress | Bug | High | 97200 | 4744 | Sprint 1 | v2.0 | refactor | Frontend | Eve | Won't Fix | 2024-03-29 | 27 | 1.32
OPS-39 | OPS | Sample issue summary 39 | Diana | 2024-02-10 | 2024-02-11 | In Progress | Story | Medium | 14400 | 2448 | Sprint 1 | v1.0 | refactor | Integration | Heidi | Fixed | 2024-03-31 | 4 | 0.68
DEV-40 | DEV | Sample issue summary 40 | Charlie | 2024-04-01 | 2024-04-10 | Review | Task | Critical | 86400 | 63762 | Sprint 3 | v2.0 | refactor | Frontend | Frank | Fixed | 2024-05-28 | 24 | 17.71
PROJ-41 | PROJ | Sample issue summary 41 | Bob | 2024-04-28 | 2024-05-05 | Done | Story | Low | 14400 | 5519 | Backlog | v1.1 | backend | API | Frank | Fixed | 2024-04-22 | 4 | 1.53
PROJ-42 | PROJ | Sample issue summary 42 | Bob | 2024-02-29 | 2024-03-07 | Review | Task | High | 133200 | 115513 | Sprint 1 | v1.0 | analytics, backend, QA | Backend | Frank | Duplicate | 2024-04-13 | 37 | 32.09
DEV-43 | DEV | Sample issue summary 43 | Alice | 2024-04-30 | 2024-05-10 | To Do | Task | Critical | 10800 | 4666 | Sprint 3 | v1.0 | UI, backend, QA | Database | Grace | Fixed | 2024-02-04 | 3 | 1.3
PROJ-44 | PROJ | Sample issue summary 44 | Bob | 2024-04-13 | 2024-04-23 | Done | Task | Critical | 118800 | 74447 | Backlog | v2.0 | QA | Frontend | Eve | Unresolved | 2024-04-19 | 33 | 20.68
DEV-45 | DEV | Sample issue summary 45 | Bob | 2024-03-15 | 2024-03-17 | Done | Story | Low | 140400 | 128304 | Sprint 2 | v2.0 | refactor, backend | Database | Eve | Unresolved | 2024-05-19 | 39 | 35.64
DEV-46 | DEV | Sample issue summary 46 | Alice | 2024-03-05 | 2024-03-13 | In Progress | Bug | Critical | 10800 | 6514 | Sprint 2 | v2.0 | analytics, urgent | API | Grace | Duplicate | 2024-04-16 | 3 | 1.81
PROJ-47 | PROJ | Sample issue summary 47 | Charlie | 2024-02-10 | 2024-02-18 | Review | Story | Low | 28800 | 21228 | Sprint 2 | v1.0 | QA, backend | Database | Grace | Duplicate | 2024-02-09 | 8 | 5.9
DEV-48 | DEV | Sample issue summary 48 | Charlie | 2024-02-27 | 2024-02-29 | In Progress | Story | Medium | 75600 | 61325 | Sprint 2 | v1.0 | analytics, QA | Frontend | Frank | Duplicate | 2024-01-22 | 21 | 17.03
PROJ-49 | PROJ | Sample issue summary 49 | Bob | 2024-04-12 | 2024-04-22 | Review | Bug | Low | 97200 | 9633 | Sprint 1 | v2.0 | QA, analytics | Database | Heidi | Won't Fix | 2024-03-11 | 27 | 2.68
PROJ-50 | PROJ | Sample issue summary 50 | Bob | 2024-03-06 | 2024-03-09 | Done | Bug | Low | 82800 | 47016 | Sprint 3 | v1.0 | urgent, QA | Frontend | Grace | Fixed | 2024-04-16 | 23 | 13.06