## Issues
Issue Key | Theme | WorkStream | TAGS | Summary | Issue Type | Parent Key | Status | Priority | Reporter | Assignee | Start Date | Due Date | Sprint | Fix Version | Original Estimate (days) | Story Points | Project
PSSDP- 1121 | Programme | Platform | POD1 | Sample issue summary 1 | Initiative |  | In Progress | High | Heidi | Divya | 2025-03-26 | 2025-07-30 |  |  |  | 3 | Lucid
PSSDP- 1122 | Programme | Platform | POD2 | Sample issue summary 2 | Initiative |  | In Progress | Medium | Eve | Divya | 2025-05-02 | 2025-08-31 |  |  |  | 13 | Snowflake
PSSDP- 1123 | Programme | Platform | POD2 | Sample issue summary 2 | Epic | PSSDP- 1122 | In Progress | Medium | Eve | Shane | 2025-05-05 | 2025-06-30 |  |  |  | 13 | Snowflake
PSSDP- 1124 | Programme | Platform | POD1 | Sample issue summary 3 | Epic | PSSDP- 1121 | In Progress | High | Heidi | Shane | 2025-03-27 | 2025-05-07 |  |  |  | 13 | Lucid
PSSDP- 1125 | Programme | Platform | POD1 | Sample issue summary 4 | Epic | PSSDP- 1121 | To Do | High | Heidi | Shane | 2025-05-08 | 2025-07-31 |  |  |  | 13 | Lucid
PSSDP- 1126 | Programme | Platform | POD1 | Sample issue summary 5 | Story | PSSDP- 1121 | Done | High | Heidi | Shane | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1127 | Programme | Platform | POD1 | Sample issue summary 5 | Story | PSSDP- 1124 | Done | High | Heidi | Bob | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1128 | Programme | Platform | POD1 | Sample issue summary 6 | Story | PSSDP- 1124 | Done | Medium | Heidi | Mark | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1129 | Programme | Platform | POD1 | Sample issue summary 7 | Story | PSSDP- 1124 | Done | High | Eve | Julie | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1130 | Programme | Platform | POD1 | Sample issue summary 8 | Story | PSSDP- 1124 | Done | Low | Heidi | Diana | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 5 | 5 | Lucid
PSSDP- 1131 | Programme | Platform | POD1 | Sample issue summary 9 | Story | PSSDP- 1124 | Done | Medium | Frank | Robert | 2025-03-27 | 2025-04-09 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1132 | Programme | Platform | POD1 | Sample issue summary 10 | Story | PSSDP- 1124 | Done | Medium | Grace | Alice | 2024-04-21 | 2025-04-23 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1133 | Programme | Platform | POD1 | Sample issue summary 11 | Story | PSSDP- 1124 | Done | Medium | Grace | Charlie | 2024-04-21 | 2025-04-23 | Sprint 1 | v1.0 | 3 | 3 | Lucid
PSSDP- 1134 | Programme | Platform | POD1 | Sample issue summary 12 | Story | PSSDP- 1124 | Done | Medium | Eve | Diana | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid
PSSDP- 1135 | Programme | Platform | POD1 | Sample issue summary 13 | Story | PSSDP- 1124 | Done | Medium | Grace | Julie | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid
PSSDP- 1136 | Programme | Platform | POD1 | Sample issue summary 14 | Story | PSSDP- 1124 | Done | Medium | Grace | Charlie | 2024-04-21 | 2025-04-23 | Sprint 2 | v2.0 | 3 | 3 | Lucid
PSSDP- 1137 | Programme | Platform | POD1 | Sample issue summary 15 | Bug | PSSDP- 1124 | Done | Medium | Grace | Bob | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 2 | 2 | Lucid
PSSDP- 1138 | Programme | Platform | POD1 | Sample issue summary 16 | Story | PSSDP- 1124 | Done | High | Eve | Mark | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid
PSSDP- 1139 | Programme | Platform | POD1 | Sample issue summary 17 | Story | PSSDP- 1124 | Done | Medium | Frank | Robert | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 5 | 5 | Lucid
PSSDP- 1140 | Programme | Platform | POD1 | Sample issue summary 18 | Story | PSSDP- 1124 | Done | Medium | Frank | Shane | 2025-04-10 | 2025-04-23 | Sprint 2 | v2.0 | 3 | 3 | Lucid
PSSDP- 1141 | Programme | Platform | POD1 | Sample issue summary 19 | Story | PSSDP- 1124 | In Progress | Critical | Grace | Mark | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid
PSSDP- 1142 | Programme | Platform | POD1 | Sample issue summary 20 | Story | PSSDP- 1124 | In Progress | Medium | Grace | Diana | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid
PSSDP- 1143 | Programme | Platform | POD1 | Sample issue summary 21 | Story | PSSDP- 1124 | In Progress | Medium | Grace | Julie | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid
PSSDP- 1144 | Programme | Platform | POD1 | Sample issue summary 22 | Story | PSSDP- 1124 | In Progress | Medium | Eve | Bob | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid
PSSDP- 1145 | Programme | Platform | POD1 | Sample issue summary 23 | Story | PSSDP- 1124 | Backlog | Medium | Heidi | Diana | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid
PSSDP- 1146 | Programme | Platform | POD1 | Sample issue summary 24 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Alice | 2025-05-05 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid
PSSDP- 1147 | Programme | Platform | POD1 | Sample issue summary 25 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Charlie | 2025-05-05 | 2025-05-07 | Sprint 3 | v3.0 | 3 | 3 | Lucid
PSSDP- 1148 | Programme | Platform | POD1 | Sample issue summary 26 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Robert | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 5 | 5 | Lucid
PSSDP- 1149 | Programme | Platform | POD1 | Sample issue summary 27 | Story | PSSDP- 1124 | Backlog | Medium | Frank | Shane | 2025-04-24 | 2025-05-07 | Sprint 3 | v3.0 | 2 | 2 | Lucid
PSSDP- 1150 | Programme | Platform | POD1 | Sample issue summary 28 | Story | PSSDP- 1125 | Backlog | High | Grace | Bob | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid
PSSDP- 1151 | Programme | Platform | POD1 | Sample issue summary 29 | Story | PSSDP- 1125 | Backlog | Medium | Grace | Diana | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid
PSSDP- 1152 | Programme | Platform | POD1 | Sample issue summary 30 | Story | PSSDP- 1125 | Backlog | Medium | Grace | Julie | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1153 | Programme | Platform | POD1 | Sample issue summary 31 | Story | PSSDP- 1125 | Backlog | Medium | Eve | Bob | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1154 | Programme | Platform | POD1 | Sample issue summary 32 | Story | PSSDP- 1125 | Backlog | Medium | Heidi | Mark | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 5 | 5 | Lucid
PSSDP- 1155 | Programme | Platform | POD1 | Sample issue summary 33 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Alice | 2025-05-19 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1156 | Programme | Platform | POD1 | Sample issue summary 34 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Charlie | 2025-05-19 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1157 | Programme | Platform | POD1 | Sample issue summary 35 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Robert | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1158 | Programme | Platform | POD1 | Sample issue summary 36 | Story | PSSDP- 1125 | Backlog | Medium | Frank | Shane | 2025-05-08 | 2025-05-21 | Sprint 4 | v4.0 | 3 | 3 | Lucid
PSSDP- 1159 | Programme | Platform | POD2 | Sample issue summary 28 | Story | PSSDP- 1123 | Backlog | High | Grace | Bob | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake
PSSDP- 1160 | Programme | Platform | POD2 | Sample issue summary 29 | Story | PSSDP- 1123 | Backlog | Medium | Grace | Diana | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake
PSSDP- 1161 | Programme | Platform | POD2 | Sample issue summary 30 | Story | PSSDP- 1123 | Backlog | Medium | Grace | Julie | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake
PSSDP- 1162 | Programme | Platform | POD2 | Sample issue summary 31 | Story | PSSDP- 1123 | Backlog | Medium | Eve | Bob | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake
PSSDP- 1163 | Programme | Platform | POD2 | Sample issue summary 32 | Story | PSSDP- 1123 | Backlog | Medium | Heidi | Mark | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 5 | 5 | Snowflake
PSSDP- 1164 | Programme | Platform | POD2 | Sample issue summary 33 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Alice | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake
PSSDP- 1165 | Programme | Platform | POD2 | Sample issue summary 34 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Charlie | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake
PSSDP- 1166 | Programme | Platform | POD2 | Sample issue summary 35 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Robert | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake
PSSDP- 1167 | Programme | Platform | POD2 | Sample issue summary 36 | Story | PSSDP- 1123 | Backlog | Medium | Frank | Shane | 2025-05-05 | 2025-05-16 | Sprint 5 | v5.0 | 3 | 3 | Snowflake

## Skills
Resource | Skillset
Alice | QA
Charlie | QA
Diana | Dev
Bob | Dev
Mark | Dev
Julie | Dev
Robert | DevOps
Shane | Tech Lead
Divya | PM

## Worklogs
Issue Key | Resource | Date | Time Spent (hrs)
PSSDP- 1121 | Divya | 2025-04-03 | 4
PSSDP- 1122 | Divya | 2025-05-12 | 8
PSSDP- 1122 | Divya | 2025-05-02 | 6
PSSDP- 1122 | Divya | 2025-05-07 | 8
PSSDP- 1123 | Shane | 2025-05-13 | 2
PSSDP- 1124 | Shane | 2025-04-03 | 8
PSSDP- 1125 | Shane | 2025-05-17 | 2
PSSDP- 1126 | Shane | 2025-04-05 | 6
PSSDP- 1126 | Shane | 2025-04-06 | 2
PSSDP- 1126 | Shane | 2025-04-05 | 8
PSSDP- 1127 | Bob | 2025-03-27 | 8
PSSDP- 1128 | Mark | 2025-04-04 | 4
PSSDP- 1128 | Mark | 2025-04-06 | 4
PSSDP- 1128 | Mark | 2025-03-29 | 4
PSSDP- 1129 | Julie | 2025-03-28 | 2
PSSDP- 1130 | Diana | 2025-04-01 | 6
PSSDP- 1130 | Diana | 2025-04-04 | 8
PSSDP- 1130 | Diana | 2025-03-31 | 4
PSSDP- 1131 | Robert | 2025-03-31 | 4
PSSDP- 1131 | Robert | 2025-04-04 | 2
PSSDP- 1131 | Robert | 2025-03-29 | 2
PSSDP- 1132 | Alice | 2024-04-29 | 6
PSSDP- 1132 | Alice | 2024-04-23 | 8
PSSDP- 1133 | Charlie | 2024-04-30 | 8
PSSDP- 1133 | Charlie | 2024-04-24 | 4
PSSDP- 1133 | Charlie | 2024-04-30 | 4
PSSDP- 1134 | Diana | 2025-04-13 | 6
PSSDP- 1135 | Julie | 2025-04-17 | 4
PSSDP- 1136 | Charlie | 2024-04-25 | 8
PSSDP- 1136 | Charlie | 2024-04-24 | 8
PSSDP- 1137 | Bob | 2025-04-17 | 4
PSSDP- 1137 | Bob | 2025-04-19 | 4
PSSDP- 1138 | Mark | 2025-04-20 | 8
PSSDP- 1139 | Robert | 2025-04-15 | 8
PSSDP- 1139 | Robert | 2025-04-14 | 2
PSSDP- 1139 | Robert | 2025-04-10 | 6
PSSDP- 1140 | Shane | 2025-04-11 | 8
PSSDP- 1140 | Shane | 2025-04-12 | 8
PSSDP- 1140 | Shane | 2025-04-19 | 6
PSSDP- 1141 | Mark | 2025-04-28 | 6
PSSDP- 1142 | Diana | 2025-04-25 | 8
PSSDP- 1142 | Diana | 2025-05-01 | 2
PSSDP- 1143 | Julie | 2025-05-04 | 8
PSSDP- 1143 | Julie | 2025-05-02 | 2
PSSDP- 1143 | Julie | 2025-05-02 | 4
PSSDP- 1144 | Bob | 2025-04-27 | 8
PSSDP- 1144 | Bob | 2025-05-02 | 8
PSSDP- 1144 | Bob | 2025-04-30 | 2
PSSDP- 1145 | Diana | 2025-05-01 | 2
PSSDP- 1146 | Alice | 2025-05-14 | 4
PSSDP- 1147 | Charlie | 2025-05-10 | 2
PSSDP- 1147 | Charlie | 2025-05-07 | 8
PSSDP- 1147 | Charlie | 2025-05-05 | 2
PSSDP- 1148 | Robert | 2025-04-28 | 2
PSSDP- 1149 | Shane | 2025-04-27 | 8
PSSDP- 1149 | Shane | 2025-04-24 | 2
PSSDP- 1149 | Shane | 2025-04-26 | 8
PSSDP- 1150 | Bob | 2025-05-09 | 8
PSSDP- 1150 | Bob | 2025-05-15 | 2
PSSDP- 1151 | Diana | 2025-05-08 | 8
PSSDP- 1152 | Julie | 2025-05-15 | 4
PSSDP- 1152 | Julie | 2025-05-10 | 2
PSSDP- 1152 | Julie | 2025-05-10 | 4
PSSDP- 1153 | Bob | 2025-05-14 | 6
PSSDP- 1154 | Mark | 2025-05-11 | 2
PSSDP- 1154 | Mark | 2025-05-10 | 2
PSSDP- 1155 | Alice | 2025-05-23 | 2
PSSDP- 1155 | Alice | 2025-05-24 | 6
PSSDP- 1156 | Charlie | 2025-05-26 | 4
PSSDP- 1156 | Charlie | 2025-05-21 | 6
PSSDP- 1157 | Robert | 2025-05-09 | 2
PSSDP- 1158 | Shane | 2025-05-15 | 2
PSSDP- 1158 | Shane | 2025-05-14 | 2
PSSDP- 1159 | Bob | 2025-05-08 | 6
PSSDP- 1159 | Bob | 2025-05-06 | 8
PSSDP- 1159 | Bob | 2025-05-05 | 6
PSSDP- 1160 | Diana | 2025-05-06 | 4
PSSDP- 1160 | Diana | 2025-05-12 | 4
PSSDP- 1161 | Julie | 2025-05-07 | 8
PSSDP- 1161 | Julie | 2025-05-13 | 2
PSSDP- 1162 | Bob | 2025-05-13 | 6
PSSDP- 1162 | Bob | 2025-05-11 | 4
PSSDP- 1163 | Mark | 2025-05-05 | 8
PSSDP- 1163 | Mark | 2025-05-08 | 4
PSSDP- 1163 | Mark | 2025-05-13 | 2
PSSDP- 1164 | Alice | 2025-05-09 | 8
PSSDP- 1165 | Charlie | 2025-05-05 | 8
PSSDP- 1165 | Charlie | 2025-05-09 | 6
PSSDP- 1166 | Robert | 2025-05-13 | 4
PSSDP- 1167 | Shane | 2025-05-12 | 2
PSSDP- 1167 | Shane | 2025-05-14 | 4

## Non_Availability
Date | Resource | Reason
2025-05-06 | Alice | Sick
2025-04-24 | Charlie | Training
2025-05-15 | Diana | Training
2025-05-06 | Diana | Holiday
2025-04-17 | Bob | Training
2025-05-12 | Mark | Holiday
2025-05-02 | Julie | Holiday
2025-05-11 | Julie | Training
2025-05-12 | Robert | Leave
2025-04-28 | Shane | Sick
2025-05-01 | Shane | Training
2025-05-11 | Divya | Sick